## Asset Retirement MProj 25-30
Area Plan Project | Asset Category | Description | Retirement year | Area | New Retirement? | Changes from DTAPR 2024 | Reasons for change | Distribution / Dual Function
PR_1.1.0026 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 928/3 & 929/1 LANE COVE STSS - DALLEY ST ZN | 2026 | Inner Metro | No | Yes | Project timing adjustment. | Distribution
PR_1.1.0028A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 9SA & 92P BEACONSFIELD - CAMPBELL ST ZN & BELMORE PK ZN | 2026 | Inner Metro | No | Yes | Project timing adjustment. | Dual Function
PR_1.1.0029A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91X/2 & 91Y/2 CHULLORA STSS - MARRICKVILLE ZN | 2032 | Inner Metro | No | Yes | Project timing adjustment to align with Transgrid PSF Stage 2. Maintained due to previous reporting. | Dual Function
PR_1.1.0030A | 131 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91A/1 & 91B/1 BEACONSFIELD BSP - ST PETERS ZN | 2032 | Inner Metro | No | Yes | Project timing adjustment. | Dual Function
PR_1.1.0034A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 92X & 92C CHULLORA STSS - ST PETERS ZN | 2032 | Inner Metro | No | Yes | Project timing adjustment to align with Transgrid PSF Stage 2. Maintained due to previous reporting. | Dual Function
PR_1.1.0045A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 91X/1 & 91Y/1 BEACONSFIELD BSP - MARRICKVILLE ZN | 2032 | Inner Metro | No | Yes | Project timing adjustment. | Dual Function
PR_1.1.0110 | 132 kV Underground Cable (Oil Filled Type) x 3 | RETIRE 132KV FEEDERS 91L, 91M & 91M/3 PEAKHURST STS - BUNNERONG STSS | 2026 | Inner Metro | No | Yes | Project timing adjustment. | Dual Function
PR_1.1.0111 | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDERS 9FF BEACONSFIELD BSP - MILL POND RD | 2032 | Inner Metro | No | Yes | Project timing adjustment. | Dual Function
PR_1.4.0037A | STS Switchgear 33kV (Oil) - Circuit Breaker x 24 | RETIRE 33KV SWITCHGEAR MEREWETHER 132/33KV STS | 2030 | Lower Hunter Transmission | No | Yes | Project timing adjustment. | Distribution
PR_1.4.0037A | STS Switchroom Building | RETIRE 33KV SWITCHGEAR MEREWETHER 132/33KV STS | 2030 | Lower Hunter Transmission | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0017 | 132 kV Underground Cable (Oil Filled Type) x 4 | RETIRE 132KV FEEDERS 929/2, 92L/1, 928/1 & 92M/2 SURRY HILLS STS - DALLEY ST ZN | 2026 | Sydney CBD | No | No |  | Distribution
PR_2.1.0127 | Zone Substation Building | RETIRE CITY EAST 33/11kV ZN & ASSOCIATED 33KV FEEDERS | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone CLC equipment (Mechanical) x 3 | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone General (including spares) | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone Switchgear 132kV (Gas) - Circuit Breakers x 7 | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone Switchgear 11kV (Oil) - Circuit Breakers x 53 | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone Transformers - 132/11kV (Gas) - (<=100 MVA) x 1 | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone Transformers - 132/11kV (Oil) - (<=100 MVA) x 3 | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_2.1.0134A | Zone Substation Building | RETIRE DALLEY ST 132/11KV ZN | 2026 | CBD | No | Yes | Project timing adjustment. | Distribution
PR_3.1A.0029A | 33 kV Underground Cables (Gas-Filled Type) x 2 | RETIRE DARLINGHURST 33KV FEEDERS 386 & 389 | 2028 | Eastern suburbs | No | No |  | Distribution
PR_3.1B.0017 | 33 kV Underground Cables (HSL Type) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2032 | Eastern suburbs | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_3.1B.0017 | Zone CLC equipment (Mechanical) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2032 | Eastern suburbs | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_3.1B.0017 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 25 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2032 | Eastern suburbs | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_3.1B.0017 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 2 | RETIRE 11KV COMPOUND SWITCHGEAR & ASSOCIATED 33kV FEEDERS MASCOT 33/11KV ZN | 2032 | Eastern suburbs | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_3.1B.0032A | Zone Switchgear 11kV (VCB) - Circuit Breakers x 9 | RETIRE 11KV COMPOUND SWITCHGEAR BOTANY 33/11KV ZN | 2029 | Eastern suburbs | No | Yes | Project timing adjustment. | Distribution
PR_3.1B.0034A | Zone Switchgear 33kV (Oil) - Circuit Breaker | RETIRE 33KV SWITCHGEAR SYDNEY DOMESTIC 33/11KV ZN | 2026 | Eastern suburbs | No | Yes | Project timing adjustment. | Distribution
PR_3.1C.0030 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 260/1 & 261/1 BEACONSFIELD BSP - ZETLAND ZN | 2026 | Eastern suburbs | No | Yes | Project timing adjustment. | Distribution
PR_3.1C.0038A | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDER 264 BEACONSFIELD BSP - KINGSFORD ZN | 2026 | Eastern suburbs | No | No |  | Dual Function
PR_4.1.0007 | 33 kV Underground Cables (Gas-Filled Type) x 2 | RETIRE 33KV FEEDERS 769 & 770 PEAKHURST STS - BLAKEHURST ZN | 2030 | St George | No | No |  | Distribution
PR_4.1.0007 | Zone General (including spares) | RETIRE BLAKEHURST 33/11KV ZN | 2030 | St George | Yes | Yes | Change of preferred option to single stage retirement | Distribution
PR_4.1.0007 | Zone Switchgear 11kV (Oil) - Circuit Breakers x 13 | RETIRE BLAKEHURST 33/11KV ZN | 2030 | St George | Yes | Yes | Change of preferred option to single stage retirement | Distribution
PR_4.1.0007 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 3 | RETIRE BLAKEHURST 33/11KV ZN | 2030 | St George | Yes | Yes | Change of preferred option to single stage retirement | Distribution
PR_4.1.0007 | Zone Substation Building | RETIRE BLAKEHURST 33/11KV ZN | 2030 | St George | Yes | Yes | Change of preferred option to single stage retirement
PR_4.1.0029 | STS Switchroom Building | RETIRE 33KV SWITCHGEAR PEAKHURST 132/33KV STS | 2026 | St George | No | Yes | Project timing adjustment. | Distribution
PR_4.3B.0008 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 15 | RETIRE 11KV SWITCHGEAR MILPERRA 33/11KV ZN | 2028 | Canterbury Bankstown | No | Yes | Project timing adjustment. | Distribution
PR_4.4.B.0002 | 33 kV Underground Cables (HSL Type) x 3 | RETIRE 33KV FEEDERS HSL SECTIONS 607, 608 & 609 HOMEBUSH STS - CONCORD ZN | 2028 | Inner West | No | Yes | Project timing adjustment. | Distribution
PR_4.4.B.0002 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 26 | RETIRE 11KV SWITCHGEAR CONCORD 33/11KV ZN | 2028 | Inner West | No | Yes | Project timing adjustment. | Distribution
PR_4.4.B.0002 | Zone Substation Building | RETIRE 11KV SWITCHGEAR CONCORD 33/11KV ZN | 2028 | Inner West | No | Yes | Project timing adjustment. | Distribution
PR_4.4.B.0010 | 132 kV Underground Cable (Oil Filled Type) x 1 | RETIRE 132KV FEEDER 90L MASON PARK STSS - HOMEBUSH STS | 2026 | Inner West | No | Yes | Project timing adjustment. | Distribution
PR_4.4.B.0022A | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 923/2 & 924/2 MASON PARK STSS - BURWOOD ZN | 2026 | Inner West | No | Yes | Project timing adjustment. | Distribution
PR_4.5.0006 | Zone CLC equipment (Mechanical) x 3 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2026 | Camperdown Blackwattle Bay | No | Yes | Project timing adjustment. | Distribution
PR_4.5.0006 | Zone General (including spares) | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2026 | Camperdown Blackwattle Bay | No | Yes | Project timing adjustment. | Distribution
PR_4.5.0006 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 33 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2026 | Camperdown Blackwattle Bay | No | Yes | Project timing adjustment. | Distribution
PR_4.5.0006 | Zone Transformers - 33/11kV (Oil) - (>15MVA & <= 40MVA) x 4 | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2026 | Camperdown Blackwattle Bay | No | Yes | Project timing adjustment. | Distribution
PR_4.5.0006 | Zone Substation Building | RETIRE BLACKWATTLE BAY 33/5KV ZN | 2026 | Camperdown Blackwattle Bay | No | Yes | Project timing adjustment. | Distribution
PR_5.1.0035A | STS Switchgear 33kV (Oil) - Circuit Breaker x 28 | RETIRE 33KV SWITCHGEAR WILLOUGHBY 132/33KV STS | 2032 | Lower North Shore | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_5.1.0035A | STS Switchroom Building | RETIRE 33KV SWITCHGEAR WILLOUGHBY 132/33KV STS | 2032 | Lower North Shore | No | Yes | Project timing adjustment. Maintained due to previous reporting. | Distribution
PR_5.2.0019 | 132 kV Underground Cable (Oil Filled Type) x 2 | RETIRE 132KV FEEDERS 9E1 & 9E2 SYDNEY EAST BSP - KURINGAI STS | 2028 | Upper North Shore | No | Yes | Project timing adjustment. | Distribution
PR_7.4.0002 | 33kV Wood Lines Mains Conductor & Accessories | RETIRE 33KV REDUNDANT NETWORK AWABA 132/33KV STS | 2026 | West Lake Macquarie | No | Yes | Project timing adjustment. | Distribution
PR_7.6.0014 | Zone Switchgear 11kV (Oil) - Circuit Breaker x 12 | RETIRE 11kV SWITCHGEAR TARRO 33/11KV ZN | 2026 | Maitland | No | Yes | Project timing adjustment. | Distribution
| Methodology | Cost Benefit analysis carried out for alternative options to satisfy identified needs. Value of unserved energy from an interruption to supply is estimated based on the probabilities of items of equipment being unavailble for service. Other factors considered include safety, environmental risks and change in maintenance costs.
| Additional Notes | The dates listed in the retirement year column are indicative of the electrical disconnection and decommission of the corresponding network assets. This may defer from the dates indicated in Chapters 5, 6 and 7 of the DTAPR document because the latter indicates date expected completion or the date when the network issue is addressed.